## Sheet1
Freehold-Title-Free from encumbrances (VPL)
No. | Description | Est. Time | From Date | Start After Task
1 | Obtain Purchaser IC, Vendor's IC, Booking Form, Previous SPA, Title, Address, Title Search | 1 | Date Open File | 0
2 | If The Assessment Receipt And Quit Rent Is Less Than 4 Months Validity Ask Vendor To Pay The Next Bill. This Is To Avoid Delay. | 1 | Date Open File | 0
3 | Prepare SPA, MOT, CKHT 1A, 2A And 3, Vendor's SD And Undertaking, Entry And Withdrawal Of Private Caveat, SD For Reduction Of Stamp Duty, Borang I , Change Of Address Form (Borang 20) And Tax Invoice (Complete Within 5 Days). During signing prepare consent to transfer. | 5 | Start After Task | 2
4 | SPA And Bankruptcy/Winding Up Search Complete And Arrange For Signing | 2 | Start After Task | 3
5 | SPA Signed, Stamped And Forwarded To Vendor, Purchaser And Emailed To Agent. Prepare Bill. Lodge Caveat. Update System On SPA Date. | 5 | Start After Task | 4
6 | Caveat Already Lodged At Land Office | 3 | SPA Date | 0
6A | Request Redemption Statement | 2 | LI Date
7 | Pay Retention Sum | 15 | SPA Date | 0
8 | File CKHT 1A And 2A | 30 | SPA Date | 0
9 | Receive Letter Instruction | 5 | SPA Date | 0
10 | Customer Execute Loan Documents And Request Confirmation From SPA Solicitor | 5 | Start After Task | 9
11 | Forward Loan Documents To Bank For Execution | 3 | Start After Task | 10
12 | Received Loan Documents Executed By Bank Without Amendments. | 7 | Start After Task | 11
13 | Adjudicate MOT & Loan Documents, Settle Differential Sum And Payment For Tax Invoice. Forward Bank's Undertaking To Vendor's Lawyer. Lodge Bank's Caveat and conduct land search. | 5 | Start After Task | 12
13A | Advise for Drawdown (Redemption) | 3 | Start After Task
13B | Receive Redemption Sum and Key-in Redemption Date. Stamped Loan Documents and MOT. | 7 | Start After Task
14 | Stamp MOT & Loan Documents (<- remove this). Present For Transfer And Charge. | 20 | After Redemption Date | 13
15 | Advise For Drawdown (final drawdown). Notify Parties to get ready on delivery of keys. | 3 | Start After Task | 14
16 | Notify Parties That That The Bank Already Released The Loan, Delivery Of Keys And Apportionment Outgoings. | 5 | Start After Task | 15
17 | Inform Management Of Change Of Ownership (If Applicable) | 3 | Start After Task | 16
18 | Return Title To The Bank And Give A Copy Of The Customer Together A Duly Stamped Loan Documents. | 14 | Start After Task | 16
19 | Received Acknowledgement And Inform Superior To Close File & File Borang 20 (Change Of Address). Scanned A Copy Of Acknowledgement Into File Folder. | 5 | Start After Task | 18
20 | File Borang I | 30 | SPA Date | 0
21 | Update Parties on the status 1st | 15 | SPA Date
22 | Update Parties on the status 2nd | 15 | After task
23 | Update Parties on the status 3rd | 20 | After task
24 | Update Parties on the status 4th | 20 | After task
25 | Update Parties on the status 5th | 20